## I&T
|  |  |  | Work Package Title | Tasks | Labor Type | Total Days | Total Hours | Total Cost |  | Engineer | Base hours charge
[11 empty] | CE=Chief Eng | 100
[9 empty] | 4138400 |  | SE = System Eng | 75
1.5 |  |  |  | Install, I&T |  |  |  | 19160 |  |  | Swe = Software Eng | 80
| 1.5.1 |  |  | Test Software & Hardware |  |  |  | 14440 |  |  | Set= Software Tester | 70
|  | 1.5.1.1 |  | Software Design |  |  |  | 440
|  |  | 1.5.1.1.1 | Software Requirement specification |  | CE | 5 | 200 | 20000
|  |  | 1.5.1.1.2 | Software work package definiton |  | CE | 3 | 120 | 12000
|  |  | 1.5.1.1.3 | Software Unit Detailed Design |  | CE | 3 | 120 | 12000
|  | 1.5.1.2 |  | Software Build |  |  |  | 8000
|  |  | 1.5.1.2.1 | Software Unit Coding |  | CE | 5 | 7600 | 760000
|  |  | 1.5.1.2.2 | Software Unit Debugging |  | CE | 10 | 400 | 40000
|  | 1.5.1.3 |  | Unit Testing |  |  |  | 7200
|  |  | 1.5.1.3.1 | Unit Test Planning |  | Set | 5 | 6400 | 448000
|  |  | 1.5.1.3.2 | Unit Test Case Prepration |  | Set | 5 | 200 | 14000
|  |  | 1.5.1.3.3 | Unit Test Conduct |  | Set | 10 | 400 | 28000
|  |  | 1.5.1.3.4 | Unit Test Records |  | Set | 5 | 200 | 140000
|  | 1.5.1.4 |  | Hardware Build |  |  |  | 4000
|  |  | 1.5.1.4.1 | Hardware Requirement Planning |  | SE | 10 | 400 | 30000
|  |  | 1.5.1.4.2 | Hardware System Defination |  | Swe | 20 | 800 | 640000
|  |  | 1.5.1.4.3 | Hardware component selection |  | SE | 10 | 400 | 30000
|  |  | 1.5.1.4.4 | Hardware Unit/component Testing |  | SE | 10 | 2400 | 180000
| 1.5.2 |  |  | Prototype Development |  |  |  | 4720
|  | 1.5.2.1 |  | Prototype Subsystem Fabrication, Assembly and Installation |  | Swe | 30 | 1200 | 96000
|  | 1.5.2.2 |  | Prototype Fabrication and Assembly |  | Swe | 20 | 800 | 640000
|  | 1.5.2.3 |  | Prototype Installation |  | SE | 10 | 400 | 30000
|  | 1.5.2.4 |  | Training for Prototype Operational Testing |  | CE |  | 2320
| 1.5.3 |  |  | Develop Training
|  | 1.5.4.1 |  | Installation Planning |  |  |  | 3240
|  |  | 1.5.4.1.1 | User support documentation |  | SE | 5 | 200 | 150000
|  |  | 1.5.4.1.2 | User communication and training |  | SE | 15 | 1520 | 114000
|  |  | 1.5.4.1.3 | Installation Testing and verfication |  | SE | 33 | 1320 | 99000
|  |  | 1.5.4.1.4 | Installation performance monitoring |  | SE | 5 | 200 | 15000
| 1.5.4 |  |  | System Testing |  |  |  | 800
|  | 1.5.4.1 |  | Requirements Verification |  | SE | 5 | 200 | 15000
|  |  | 1.5.4.1.1 | Requirements Verification and Traceability Matrix (RVTM) |  | SE | 5 | 200 | 15000
|  |  | 1.5.4.1.2 | RVTM Traceability |  | SE | 10 | 400 | 30000
|  | 1.5.4.2 |  | Development Test and Evaluation |  |  |  | 640
|  |  | 1.5.4.2.1 | System Test Planning |  | Set | 7 | 280 | 19600
|  |  | 1.5.4.2.2 | Test Configuration Controls |  | Set | 4 | 160 | 12800
|  |  | 1.5.4.2.3 | Defect classification tracking and metrics |  | Set | 5 | 200 | 160000
| 1.5.5 |  |  | After Action Reports |  |  |  | 3000
|  |  | 1.5.5.1.1 | Document Lessons learnt |  | CE | 9 | 360 | 36000
|  |  | 1.5.5.1.2 | Archive project artificats |  | CE | 5 | 200 | 20000
|  |  | 1.5.5.1.3 | Document testing and installation results |  | CE | 11 | 440 | 44000
|  |  | 1.5.5.1.4 | Record employee training sessions for re use |  | CE | 25 | 1000 | 100000
|  |  | 1.5.5.1.5 | Conduct Meetings |  | CE | 25 | 1000 | 100000
| 1.5.6 |  |  | Report Results |  |  |  | 880
|  |  | 1.5.6.1.1 | Develop Testing Reports |  | CE | 10 | 400 | 40000
|  |  | 1.5.6.1.2 | Review Test Result |  | CE | 3 | 120 | 12000
|  |  | 1.5.6.1.3 | Conduct Closeout meeting |  | CE | 2 | 80 | 8000
|  |  | 1.5.6.1.4 | Create Closeout reports |  | CE | 5 | 200 | 20000
|  |  | 1.5.6.1.5 | Project Report |  | CE | 2 | 80 | 8000
Develop Training